## All Issues
Issue ID | Title | Category | Sub-Category | Source | Found By | Priority | Status | Sprint | Component | Affected Files | ClickUp Link | Created Date | Resolved Date | Resolution (days) | Resolved By | Description | Solution Applied | Testing Done | Deployment Status | Version | Notes
001 | Task Completion Validation | Backend | Bug Fix | Manual Testing | Developer | High | Resolved | Sprint 1 | Backend API, React Web | backend/routes/tasks.js, frontend-web/src/components/TaskDetailModal.jsx, frontend-web/src/api.js | https://app.clickup.com/t/86d1x1qdu | 2026-02-15 | 2026-02-15 | 1 | Development Team | Parent tasks could be marked complete even when subtasks remained incomplete, causing data integrity issues and user confusion. | Added backend hasIncompleteSubtasks() guard, frontend warning modal with override, and force_complete API parameter. Handles both inline (JSONB) and relational subtasks. | Unit tests for inline + relational subtasks, force_complete override, mobile tested | Pending | v1.1.0
002 | UI Alterations — Task Cards & Mobile UX | Frontend Web | Enhancement | User Report | Developer | Medium | Resolved | Sprint 4 | React Web, Design System | frontend-web/src/components/Tasks.jsx, frontend-web/src/components/Tasks.css, frontend-web/src/components/TaskDetailModal.jsx, frontend-web/src/components/BidirectionalSwipeCard.jsx, frontend-web/src/components/BottomNav.css | https://app.clickup.com/t/86d1vpb9y | 2026-02-15 | 2026-02-15 | 1 | Development Team | UI needed general improvements: task card visual polish, subtask progress indicators, swipe sensitivity, and mobile touch targets. | Added subtask progress badges, progress bars, bulk actions, improved swipe thresholds, larger touch targets in BottomNav. | Manual testing, mobile (Android), desktop, responsive design, basic accessibility review | Pending | v1.1.0
003 | Secure Vault — Encrypted Personal Details Storage | Security | New Feature | User Report | Developer | High | Resolved | Sprint 2 | Backend API, Database, React Web | backend/database.js, backend/utils/encryption.js, backend/routes/notes.js, frontend-web/src/components/VaultPage.jsx, frontend-web/src/components/VaultUnlockModal.jsx, frontend-web/src/components/AppLock.jsx, frontend-web/src/contexts/SecurityContext.jsx | https://app.clickup.com/t/86d1uwmu2 | 2026-02-15 | 2026-02-15 | 1 | Development Team | Users needed secure storage for sensitive personal data (bank details, personal numbers, credentials) with encryption at rest. | Extended notes system with AES-256-GCM encryption + PBKDF2 key derivation (100k iterations). Added VaultPage UI with auto-lock after 5 minutes. Password never stored. | Encryption/decryption cycle, password derivation, auth tag validation, auto-lock, error handling | Pending | v1.1.0 | Master password is NOT recoverable by design
004 | Skills Tracking Feature | Backend | New Feature | ClickUp | Developer | Medium | Resolved | Sprint 3 | Backend API, Database, React Web | backend/database.js, backend/routes/skills.js, backend/routes/tasks.js, backend/server.js, frontend-web/src/components/SkillsPage.jsx, frontend-web/src/components/SkillCard.jsx, frontend-web/src/components/SkillSelector.jsx, frontend-web/src/api.js, frontend-web/src/App.jsx | https://app.clickup.com/t/86d1z2736 | 2026-02-15 | 2026-02-15 | 1 | Development Team | Users needed a way to track personal skills development, link skills to tasks/study sessions, and monitor proficiency over time. | New skills / task_skills / session_skills DB tables, full CRUD API, SkillsPage dashboard, 4-level proficiency tracking, 6 categories, auto-update last_used on task completion. | CRUD operations, task-skill linking, proficiency updates, auto-update on completion, mobile responsive | Pending | v1.1.0
UI-01 | Touch Targets Too Small (<44px) | Flutter Mobile | Accessibility | AI Analysis | AI Assistant | Critical | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/ui/widgets/vela_modal.dart, vela_flutter/lib/ui/widgets/vela_input.dart, vela_flutter/lib/ui/widgets/vela_button.dart, vela_flutter/lib/ui/screens/shared/app_shell.dart, vela_flutter/lib/core/theme/app_spacing.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Multiple interactive elements are below WCAG 2.5.5 minimum 44x44px touch target. Modal close=32px, bottom nav=36px tall, inputs=40px. | Wrapped modal close button, nav items, inputs, and buttons in ConstrainedBox(BoxConstraints(minWidth: 44, minHeight: 44)). Added AppSpacing.minTouchTarget = 44.0 token for future use. | Inspect widget tree: every interactive element shows minWidth/minHeight = 44. Test on physical device with finger — no accidental mis-taps. | Pending |  | WCAG Level A violation — blocks accessibility certification
UI-02 | Bottom Nav Text Too Small | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/core/theme/app_typography.dart, vela_flutter/lib/ui/screens/shared/app_shell.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Bottom navigation label text is too small to read comfortably on mobile screens. | Added AppTypography.fontSizeNavLabel = 11.0 and navLabel() style factory with fontWeight always weightSemibold (w600). app_shell.dart uses navLabel() for all nav items. | Open app on device, check bottom nav labels are clearly legible at arm's length. Verify all labels (active and inactive) render at 11px w600. | Pending
UI-03 | Missing Onboarding Flow | Flutter Mobile | UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/shared/onboarding_tooltips.dart, vela_flutter/lib/app.dart, vela_flutter/lib/core/storage/local_storage.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | No onboarding screens to guide new users through creating a subject and logging their first session. | OnboardingTooltips widget (3-step walkthrough: swipe gestures, camera, share target) wired into app.dart via _OnboardingOverlay in the MaterialApp.router builder. Shown once per device using LocalStorage.hasSeenOnboarding flag. Respects OS reduced-motion preference. | Clear app data, launch fresh, verify 3-step tooltip sequence appears. Complete walkthrough, relaunch — confirm tooltips do not reappear. Enable OS reduced motion — confirm overlay is skipped. | Pending
UI-04 | No Back-Button Navigation | Flutter Mobile | Navigation | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/widgets/detail_header.dart, vela_flutter/lib/ui/screens/tasks/task_detail_modal.dart, vela_flutter/lib/ui/screens/sessions/add_session_modal.dart, vela_flutter/lib/ui/screens/notes/add_note_modal.dart, vela_flutter/lib/ui/screens/tasks/add_task_modal.dart, vela_flutter/lib/ui/screens/attachments/add_attachment_modal.dart, vela_flutter/lib/ui/screens/goals/add_goal_modal.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Detail screens lack a visible back button, relying solely on the Android hardware back gesture. | DetailHeader widget with ≥ 44px back button added to task_detail_modal.dart. Close buttons with ConstrainedBox(minWidth: 44, minHeight: 44) and Semantics labels added to all modal title rows in add_session_modal.dart, add_note_modal.dart, add_task_modal.dart, add_attachment_modal.dart, and add_goal_modal.dart. | Open each modal, verify close button is visible and tap target is at least 44×44px. Verify VoiceOver/TalkBack announces 'Close' button. Tap close — confirm modal dismisses correctly. | Pending
UI-05 | Share Modal — No Active Subject Indicator | Flutter Mobile | UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/attachments/share_receive_screen.dart (new), vela_flutter/lib/ui/navigation/app_router.dart, vela_flutter/lib/main.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | When sharing content from another app to Vela, the modal doesn't show which subject is currently active. | Created ShareReceiveScreen that handles share_handler intents. Displays active subject as a prominent green badge (or an amber warning when no subject is selected). User can save as Task or Attachment. Route /share-receive added to GoRouter outside the shell. main.dart detects share intent at startup and overrides initialLocationProvider to navigate there directly. | Share a URL from Chrome/YouTube to Vela. Verify ShareReceiveScreen opens. Verify active subject badge shows the correct subject name. Remove active subject, reshare — verify amber warning appears. Tap 'Task' — confirm task created in tasks screen. Tap 'Attachment' — confirm attachment saved in attachments screen. | Pending
UI-06 | Generic / Unhelpful Error Messages | Flutter Mobile | UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/core/utils/error_messages.dart, vela_flutter/lib/ui/widgets/vela_error_message.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/goals/add_goal_modal.dart, vela_flutter/lib/ui/screens/tasks/add_task_modal.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Error states show generic messages that don't tell the user what went wrong or what to do next. | Populated error_messages.dart with specific actionable strings per resource; replaced all generic catch-block texts across goals, tasks, notes, sessions screens; added VelaScreenError full-screen error widget; wired inline title error in add_task_modal using VelaInput error prop. | Manually trigger load failure on GoalsScreen — should show 'Couldn't load goals. Pull down to retry.' Submit AddTaskModal with empty title — should show inline error text below field. Trigger delete failure — should show specific SnackBar message. | Pending
UI-07 | Skeleton Loading States Missing | Flutter Mobile | Performance / UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/widgets/vela_skeleton.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/tasks/tasks_screen.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart, vela_flutter/lib/ui/screens/attachments/attachments_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | List screens show a blank/spinner while loading instead of skeleton placeholder cards. | Completed vela_skeleton.dart with VelaSkeletonGoalCard, VelaSkeleton factory class (card/listItem/text helpers), and _VelaSkeletonListItem. Replaced CircularProgressIndicator in GoalsScreen with 4x VelaSkeletonGoalCard. Tasks/Notes/Sessions/Attachments screens were already wired; confirmed consistent. Shimmer uses LinearGradient tween; respects MediaQuery.disableAnimations for reduced motion. | Open GoalsScreen with slow/offline connection — should show 4 goal-shaped skeleton cards instead of spinner. Enable OS reduce-motion — shimmer animation should stop, placeholders remain visible as flat fills. Confirm all 5 screens (tasks, notes, sessions, attachments, goals) show skeletons on load. | Pending
UI-08 | Haptic Feedback Missing | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | Low | Resolved | Backlog | Flutter App | vela_flutter/lib/core/utils/haptics.dart, vela_flutter/lib/ui/widgets/vela_button.dart, vela_flutter/lib/ui/screens/tasks/tasks_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Actions like completing a task or saving a session don't trigger haptic feedback on mobile. | Added lightTap(), mediumImpact(), heavyImpact(), and error() alias methods to VelaHaptics in haptics.dart, each try/catch guarded and gated by _isSupported. VelaButton already fires VelaHaptics.light() on press; tasks_screen already fires VelaHaptics.success() on complete and VelaHaptics.heavy() on delete — confirmed wired. | On a physical Android device: tap any VelaButton — light tap should be felt. Swipe a task card right (complete) — vibration should fire. Swipe a task card left (delete) — heavier vibration should fire. Run on web/desktop — no crash, haptics silently skipped. | Pending
UI-09 | Reduced Motion Not Supported | Flutter Mobile | Accessibility | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/core/utils/motion_preferences.dart, vela_flutter/lib/core/theme/app_animations.dart, vela_flutter/lib/ui/widgets/vela_modal.dart, vela_flutter/lib/app.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Animations do not respect the device's 'Reduce Motion' accessibility setting. | MotionPreferences.of(context) reads MediaQuery.disableAnimations. AppAnimations.baseOrNone/fastOrNone/slowOrNone return Duration.zero when reduced motion is enabled. VelaModal.show() and AnimatedContainer use these helpers; app.dart propagates the flag to onboarding overlay. | Enable 'Remove animations' (Android) or 'Reduce Motion' (iOS). Open app and verify: modals appear instantly, no fade/slide animations, onboarding overlay is skipped. | Pending |  | WCAG 2.3.3 — Animation from Interactions
UI-10 | Swipe Gesture Affordance Missing | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/tasks/tasks_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Swipeable task cards have no visual hint that they can be swiped (no drag indicator or peek animation). | Added _SwipeAffordance widget with pulsing green/red edge gradient overlays on the first active card, shown until the user first swipes (stored via localStorageProvider). Added SingleTickerProviderStateMixin and a TweenSequence peek animation controller to _TasksScreenState that translates the first card -12px then +12px then back to 0 over 300ms on first load; skipped when MediaQuery.disableAnimations is true (Issue 09 compliance). After first swipe, both the gradient overlay and peek animation are permanently dismissed. | Fresh install (or clear SharedPreferences): open tasks screen with at least one task — first card should animate left-right briefly, then show green/red edge gradients. Swipe the card — gradients disappear and don't return on next launch. Enable OS Reduce Motion — peek animation should not play; static gradients still visible. | Pending
UI-11 | Spacing Inconsistencies Across Screens | Flutter Mobile | Design System | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/ui/screens/profile/profile_screen.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/core/theme/app_spacing.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Padding and margin values are inconsistent across screens — some use 8px, 12px, 16px ad-hoc instead of design tokens. | Replaced all hardcoded padding/margin values in profile_screen.dart, goals_screen.dart, and notes_screen.dart with AppSpacing tokens (s1-s12). Added AppSpacing import to all three files. notes_screen FAB clearance updated from hardcoded 80 to AppSpacing.fabClearance + MediaQuery.of(ctx).padding.bottom. tasks_screen.dart was already clean with AppSpacing tokens. | Visual review of all four screens in light and dark mode on a physical device. Confirm consistent 16px (s4) horizontal padding on all list/card containers. Confirm FAB does not overlap the last list item on iPhone X+ and Android gesture nav devices. No pixel overflow or clipped content. | Pending
CU-001 | No Edit Option for Attachments | Frontend Web | Bug | ClickUp | User | Medium | Open | Backlog | React Web | frontend-web/src/components/ | https://app.clickup.com/t/86d28hqa6 | 2026-03-22 |  |  |  | Vela App: No edit option available for attachments — users can add attachments but cannot modify them after creation. |  |  | Not Started |  | Only OPEN issue newly fetched from ClickUp
CU-002 | Note Not Saving After Creation — Disappears on Back | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 5 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d27kyx0 | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | After creating a note, Save button just reloads the notes list. Clicking Back causes the note to disappear — not persisted to DB. | Fixed save handler to await API call and refresh note list after success. | Manual: create note, save, navigate away and back — note persists. | Pending | v1.2.0
CU-003 | Can't Scroll Through Long Note While Editing | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 5 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d27kyv6 | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | Cannot scroll through a note while editing it — notes with >1000 words are inaccessible below the fold. | Set overflow-y: auto on the note editor textarea/container. | Manual: open note with 1000+ words, verify scrolling works in edit mode. | Pending | v1.2.0
CU-004 | Remove Blue Color From Dark Theme | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 4 | React Web, Design System | frontend-web/src/design-system/tokens/ | https://app.clickup.com/t/86d27kutb | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | Blue accent color bleeds into dark theme — should use a neutral or theme-appropriate color instead. | Updated --nds-* color tokens for dark theme, replaced blue with appropriate dark-mode accent. | Visual review in dark mode across all screens. | Pending | v1.2.0
CU-005 | Don't Show 'No Details Provided' / 0 for Empty Fields | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 4 | React Web | frontend-web/src/components/TaskDetailModal.jsx | https://app.clickup.com/t/86d1x1p62 | 2026-02-08 | 2026-03-08 | 28 | Gopinath R | Task detail view shows 'No details provided' and '0 files' as explicit text when fields are empty — should be hidden or shown as a subtle placeholder. | Conditionally hide empty field labels; show placeholder only on hover/focus. | Visual check: create task with no description and no attachments — verify no awkward placeholder text. | Pending | v1.1.0
CU-006 | Remove Task Type (Study, Watch) From Task Creation | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 4 | React Web | frontend-web/src/components/Tasks.jsx | https://app.clickup.com/t/86d1x1nw3 | 2026-02-08 | 2026-03-08 | 28 | Gopinath R | Task creation form shows a 'Type of task' dropdown (Study, Watch, etc.) that is confusing and unnecessary — activity types belong to sessions, not tasks. | Removed task type field from AddTaskModal and task creation API payload. | Create a task — verify no type dropdown appears. | Pending | v1.1.0
CU-007 | Need Notes Tab Feature | Frontend Web | New Feature | ClickUp | User | High | Resolved | Sprint 3 | Backend API, Database, React Web | frontend-web/src/components/NotesPage.jsx, backend/routes/notes.js | https://app.clickup.com/t/86d1umz1y | 2026-02-03 | 2026-03-08 | 33 | Gopinath R | Users need a dedicated Notes tab to create, organize, and retrieve study notes with folder structure and tags. | Built full notes feature: NotesPage.jsx, note folders, tags, inter-note linking, backend notes + note_folders + note_links routes. | Create note, add to folder, tag it, link to another note, search — all verified. | Pending | v1.1.0
CU-008 | Need Session Add Button in History Tab | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 2 | React Web | frontend-web/src/components/Timeline.jsx | https://app.clickup.com/t/86d1u9qz9 | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | No visible button to add a new study session from the history/timeline tab — users had no way to log sessions from this view. | Added Add Session floating action button to Timeline tab. | Tap Add Session → session modal opens → session saved and appears in timeline. | Pending | v1.0.0 | Tagged 'bug' in ClickUp
CU-009 | Link Tasks and Sessions to Goals | Frontend Web | New Feature | ClickUp | User | Medium | Resolved | Sprint 3 | Backend API, React Web | frontend-web/src/components/GoalsPage.jsx, backend/routes/goals.js | https://app.clickup.com/t/86d1u4atp | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | Users need to associate tasks and study sessions with specific goals to track goal progress automatically. | Added goal_tasks and goal_sessions linking in DB + UI to attach/detach from goal detail view. | Link task to goal → verify it shows in goal detail and counts toward progress. | Pending | v1.1.0
CU-010 | Need Goal Edit Option | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 3 | React Web | frontend-web/src/components/GoalsPage.jsx | https://app.clickup.com/t/86d1u4aq4 | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | Goals could be created but not edited — no edit button or inline editing in the goals list. | Added edit modal to GoalsPage with pre-filled fields and PUT /api/goals/:id endpoint. | Edit goal title, deadline, description — verify changes saved and reflected in list. | Pending | v1.1.0
CU-011 | Goals Feature Not Working in Production | Backend | Bug | ClickUp | User | High | Resolved | Sprint 3 | Backend API, DevOps | backend/routes/goals.js, backend/server.js | https://app.clickup.com/t/86d1tnnwv | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Goals feature worked locally but failed in production — likely a missing route mount or environment config issue. | Fixed route mount order in server.js and verified DB migration ran in production. | Verified goals CRUD in production environment. | Deployed | v1.0.0
CU-012 | Goals Feature Implementation | Frontend Web | New Feature | ClickUp | User | Medium | Resolved | Sprint 3 | Backend API, Database, React Web | frontend-web/src/components/GoalsPage.jsx, backend/routes/goals.js, backend/database.js | https://app.clickup.com/t/86d1tk0z6 | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Initial implementation of Goals tab — users needed to set, track, and manage long-term study objectives. | Created goals DB table, full CRUD API, GoalsPage component with progress tracking. | Create goal, link sessions/tasks, mark complete — all flows verified. | Pending | v1.0.0 | Tagged 'enchance' in ClickUp
CU-013 | Share Option Not Available in Production App | Flutter Mobile | Bug | ClickUp | User | High | Resolved | Sprint 2 | Flutter App, DevOps | vela_flutter/android/AndroidManifest.xml | https://app.clickup.com/t/86d1tff5v | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Share-to-Vela feature (share YouTube links from other apps) was missing from the production APK — intent filter not in release build. | Added share intent filter to AndroidManifest.xml and rebuilt production APK. | Share YouTube link from Chrome → Vela appears in share sheet → link captured. | Deployed | v1.0.0
CU-014 | Basic Share Feature Implementation | Flutter Mobile | New Feature | ClickUp | User | Medium | Resolved | Sprint 2 | Flutter App | vela_flutter/android/AndroidManifest.xml, vela_flutter/lib/ | https://app.clickup.com/t/86d1tcz85 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Initial implementation of Android share target — receive URLs and text from other apps and save as attachments in Vela. | Registered Android share intent filter, built share receive screen to capture and save shared content. | Share from browser, YouTube, and notes app — all content captured and saved. | Deployed | v1.0.0
CU-015 | Mobile APK Production Blank Screen Issue | Flutter Mobile | Bug | ClickUp | User | High | Resolved | Sprint 1 | Flutter App, DevOps | vela_flutter/lib/app.dart | https://app.clickup.com/t/86d1tcbnt | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Production APK showed a blank white screen on launch — app failed to initialize correctly in release mode. | Fixed release build config, ensured assets bundled correctly, resolved null-safety issues that only surfaced in release mode. | Install release APK on physical device, verify app loads correctly. | Deployed | v1.0.0
CU-016 | Add Button Showing in Wrong Location (Home / Profile Tab) | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/App.jsx, frontend-web/src/App.css | https://app.clickup.com/t/86d1tc1zy | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Floating add button was visible on Home and Profile tabs where it had no function — caused confusion. | Conditionally rendered add button only on tabs where it's relevant (Tasks, Sessions). | Navigate to Home and Profile — no add button visible. Tasks tab — button shown. | Pending | v1.0.0 | Tagged 'home tab', 'profile tab' in ClickUp
CU-017 | Email ID Showing Incorrectly in Profile Tab | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/components/ProfilePage.jsx | https://app.clickup.com/t/86d1tc1z3 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Profile tab was displaying a wrong or undefined email address for the logged-in user. | Fixed JWT payload read in profile component to correctly extract user.email. | Login, navigate to Profile — email matches account email. | Pending | v1.0.0 | Tagged 'profile tab' in ClickUp
CU-018 | Add Note Form Is Inconsistent | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 1 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d1tc0u3 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Add note form had inconsistent spacing, label alignment, and input sizing compared to other forms in the app. | Redesigned form to use design system tokens and match other modal forms. | Visual review against Tasks and Sessions modals for consistency. | Pending | v1.0.0
CU-019 | Add Task Button Overlay Drops Below Dashboard | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/components/Tasks.jsx, frontend-web/src/components/Tasks.css | https://app.clickup.com/t/86d1tc07f | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Floating 'Add Task' button was rendered below the content area on some screen sizes, hidden behind the dashboard. | Fixed z-index and position: fixed to keep button visible at all scroll positions. | Scroll task list to bottom — add button remains visible and tappable. | Pending | v1.0.0 | Tagged 'bug', 'tasks tab' in ClickUp
CU-020 | Delete Button Not Working for Tasks | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 1 | React Web, Backend API | frontend-web/src/components/Tasks.jsx, backend/routes/tasks.js | https://app.clickup.com/t/86d1tbzr1 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Delete button on task cards was unresponsive — clicking did nothing, tasks couldn't be removed. | Fixed DELETE /api/tasks/:id handler and wired delete button to API call with confirmation. | Create task, click delete, confirm — task removed from list and DB. | Pending | v1.0.0 | Tagged 'tasks tab' in ClickUp
CU-021 | Swipe Right to Delete Tasks | Frontend Web | Enhancement | ClickUp | User | Medium | Resolved | Sprint 4 | React Web | frontend-web/src/components/BidirectionalSwipeCard.jsx | https://app.clickup.com/t/86d1tbuxc | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Users requested swipe-right gesture to quickly delete tasks on mobile, instead of tapping into the detail modal. | Implemented BidirectionalSwipeCard with right-swipe delete and left-swipe complete gestures. | Swipe right on task card — delete confirmation appears and task is removed. | Pending | v1.1.0 | Tagged 'enchance' in ClickUp
CU-022 | No Session Add Button in History Tab (Backend List) | Frontend Web | Bug | ClickUp | User | Medium | Open | Backlog | React Web | frontend-web/src/components/Timeline.jsx | https://app.clickup.com/t/86d1tdavq | 2026-01-30 |  |  |  | Duplicate open ticket: no Add Session button visible in history/timeline tab. Marked as 'mobile ui bugs' in ClickUp backend list — may need re-verification in latest build. |  |  | Not Started |  | Duplicate of CU-008 which shows resolved — needs re-verification
UI-12 | Sessions Not Loading on Timeline Screen | Flutter Mobile | Bug Fix | Manual Testing | Flutter Investigator Agent | Critical | Resolved | Backlog | Flutter App | vela_flutter/lib/data/repositories/progress_repository.dart, vela_flutter/lib/providers/progress_provider.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Sessions tab permanently shows loading/error state and never displays sessions. getSessions() called ApiConstants.sessions (/progress/sessions) — a route that does not exist in the backend. Even if the URL were correct, response.data was cast directly as List, but the real endpoint GET /api/progress/:subject_id returns { sessions: [...], topics: [...], revisionItems: [...], pagination: {...} } — sessions is a nested key, not the root value. getTopics() had the same two bugs (/progress/topics + response.data as List). The provider called three separate Future.wait requests all hitting the same endpoint, tripling network traffic. | Added getProgress(subjectId) method to ProgressRepository that calls GET /api/progress/:subjectId and returns the full Map. getSessions() and getTopics() now delegate to getProgress() and extract response.data['sessions'] and response.data['topics'] respectively. ProgressNotifier.loadProgress() refactored to call getProgress() once and unpack sessions + topics from a single network response. | Open Sessions tab with an active subject — sessions list should render. Open network inspector and confirm exactly one GET /api/progress/:id request fires on load (not three). Pull-to-refresh and re-open — list reloads correctly. | Pending |  | Backend endpoint GET /api/progress/:subject_id does NOT use the standard { data: [], pagination: {} } envelope — it uses top-level keys. This is the only progress endpoint that exists for subject-scoped data.
UI-13 | Session cards not tappable — no detail view | Flutter Mobile | Bug Fix | Interaction Completeness Audit | Flutter Investigator Agent | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart (new), vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Tapping a session card on the Timeline screen did nothing. _SessionCard had onEdit and onDelete callbacks but no onTap for a detail view. Users expect tapping a card to open its detail — the missing interaction was identified by the Step 3 Interaction Completeness Audit. | Created SessionDetailModal (modelled on TaskDetailModal) showing activity type, date, duration, topics, full notes, URL/YouTube thumbnail, revision badge, and Edit/Delete actions with confirmation dialog. Added onTap prop to _SessionCard, wrapped VelaCard in GestureDetector, added _showSessionDetail() to _TimelineScreenState, and wired onTap in the SliverList builder. | Tap a session card on the Timeline screen — SessionDetailModal opens with full session info. Tap Edit — modal closes and AddSessionModal opens pre-filled. Tap Delete — confirmation dialog appears; confirm closes modal and removes session. Slidable swipe-to-delete and inline Edit/Delete buttons still work independently. | Pending
UI-14 | Session goal badge missing; attachment stub misleading | Flutter Mobile | Bug Fix | Web Parity Review | Flutter Investigator Agent | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Web parity review against Timeline.jsx found two gaps. (1) When a session has a goal_id, the web card shows a teal goal badge with the linked goal title. Neither _SessionCard nor SessionDetailModal showed this — users had no way to see which goal a session contributed to. (2) SessionDetailModal's Attachments section showed an 'Add Attachment' button that fired showSnackBar('coming soon') — actively misleading users into thinking they could add attachments when the feature is not implemented. | Fix 1 — Goal badge in SessionDetailModal: converted StatelessWidget to ConsumerWidget, resolved goalTitle via ref.watch(goalsProvider), and added a VelaBadgeVariant.success badge (flag icon + truncated title, max 140px) after the revision badge in the meta Wrap, guarded by if (goalTitle != null). Fix 2 — Attachment stub removal: replaced the OutlinedButton/snackbar with a read-only display — muted 'No attachments' text when count is 0, or a VelaBadge with paperclip icon and count when attachments exist. Fix 3 — Goal badge on _SessionCard: added optional goalTitle String? prop, resolved at SliverList build time via ref.watch(goalsProvider) (keeps _SessionCard a plain StatelessWidget), and rendered a success badge after the revision badge in the activity type row. | Create a session linked to a goal. Open the Sessions tab — _SessionCard should show a green flag badge with the goal title next to the revision badge. Tap the card — SessionDetailModal should show the same badge in the meta row. Open a session with no goal — no badge appears. Open the modal for a session with 0 attachments — 'No attachments' muted text appears instead of the Add Attachment button. For a session with attachments the count badge renders. No snackbar fires in either case. | Pending
UI-15 | SessionDetailModal 'Add Attachment' button fires no feedback | Flutter Mobile | Bug Fix | Task — Fix non-functional button | Flutter Investigator Agent | Low | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | The '+ Add Attachment' button in SessionDetailModal had an empty onPressed: () { // TODO } lambda. Tapping it produced zero visual feedback — no snackbar, no navigation, no modal. Web parity check confirmed Timeline.jsx has no equivalent button at all (attachment_count is display-only). Backend progress.js has no writable endpoint for session-attachment linking. The feature does not exist on any platform, so the button was silently swallowing taps. | Replaced the empty onPressed lambda with a ScaffoldMessenger snackbar ('Attachment linking for sessions is coming soon.', 2-second duration). The button remains visible so users know the feature is planned, but every tap now produces visible feedback. No API calls, no navigation. | Open any session detail modal. Tap '+ Add Attachment'. A snackbar should appear at the bottom of the screen with the 'coming soon' message and dismiss after 2 seconds. No crash, no silent swallow. | Pending

## Backend
Backend — 3 issue(s)
Issue ID | Title | Category | Sub-Category | Source | Found By | Priority | Status | Sprint | Component | Affected Files | ClickUp Link | Created Date | Resolved Date | Resolution (days) | Resolved By | Description | Solution Applied | Testing Done | Deployment Status | Version | Notes
001 | Task Completion Validation | Backend | Bug Fix | Manual Testing | Developer | High | Resolved | Sprint 1 | Backend API, React Web | backend/routes/tasks.js, frontend-web/src/components/TaskDetailModal.jsx, frontend-web/src/api.js | https://app.clickup.com/t/86d1x1qdu | 2026-02-15 | 2026-02-15 | 1 | Development Team | Parent tasks could be marked complete even when subtasks remained incomplete, causing data integrity issues and user confusion. | Added backend hasIncompleteSubtasks() guard, frontend warning modal with override, and force_complete API parameter. Handles both inline (JSONB) and relational subtasks. | Unit tests for inline + relational subtasks, force_complete override, mobile tested | Pending | v1.1.0
004 | Skills Tracking Feature | Backend | New Feature | ClickUp | Developer | Medium | Resolved | Sprint 3 | Backend API, Database, React Web | backend/database.js, backend/routes/skills.js, backend/routes/tasks.js, backend/server.js, frontend-web/src/components/SkillsPage.jsx, frontend-web/src/components/SkillCard.jsx, frontend-web/src/components/SkillSelector.jsx, frontend-web/src/api.js, frontend-web/src/App.jsx | https://app.clickup.com/t/86d1z2736 | 2026-02-15 | 2026-02-15 | 1 | Development Team | Users needed a way to track personal skills development, link skills to tasks/study sessions, and monitor proficiency over time. | New skills / task_skills / session_skills DB tables, full CRUD API, SkillsPage dashboard, 4-level proficiency tracking, 6 categories, auto-update last_used on task completion. | CRUD operations, task-skill linking, proficiency updates, auto-update on completion, mobile responsive | Pending | v1.1.0
CU-011 | Goals Feature Not Working in Production | Backend | Bug | ClickUp | User | High | Resolved | Sprint 3 | Backend API, DevOps | backend/routes/goals.js, backend/server.js | https://app.clickup.com/t/86d1tnnwv | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Goals feature worked locally but failed in production — likely a missing route mount or environment config issue. | Fixed route mount order in server.js and verified DB migration ran in production. | Verified goals CRUD in production environment. | Deployed | v1.0.0

## Frontend Web
Frontend Web — 19 issue(s)
Issue ID | Title | Category | Sub-Category | Source | Found By | Priority | Status | Sprint | Component | Affected Files | ClickUp Link | Created Date | Resolved Date | Resolution (days) | Resolved By | Description | Solution Applied | Testing Done | Deployment Status | Version | Notes
002 | UI Alterations — Task Cards & Mobile UX | Frontend Web | Enhancement | User Report | Developer | Medium | Resolved | Sprint 4 | React Web, Design System | frontend-web/src/components/Tasks.jsx, frontend-web/src/components/Tasks.css, frontend-web/src/components/TaskDetailModal.jsx, frontend-web/src/components/BidirectionalSwipeCard.jsx, frontend-web/src/components/BottomNav.css | https://app.clickup.com/t/86d1vpb9y | 2026-02-15 | 2026-02-15 | 1 | Development Team | UI needed general improvements: task card visual polish, subtask progress indicators, swipe sensitivity, and mobile touch targets. | Added subtask progress badges, progress bars, bulk actions, improved swipe thresholds, larger touch targets in BottomNav. | Manual testing, mobile (Android), desktop, responsive design, basic accessibility review | Pending | v1.1.0
CU-001 | No Edit Option for Attachments | Frontend Web | Bug | ClickUp | User | Medium | Open | Backlog | React Web | frontend-web/src/components/ | https://app.clickup.com/t/86d28hqa6 | 2026-03-22 |  |  |  | Vela App: No edit option available for attachments — users can add attachments but cannot modify them after creation. |  |  | Not Started |  | Only OPEN issue newly fetched from ClickUp
CU-002 | Note Not Saving After Creation — Disappears on Back | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 5 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d27kyx0 | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | After creating a note, Save button just reloads the notes list. Clicking Back causes the note to disappear — not persisted to DB. | Fixed save handler to await API call and refresh note list after success. | Manual: create note, save, navigate away and back — note persists. | Pending | v1.2.0
CU-003 | Can't Scroll Through Long Note While Editing | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 5 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d27kyv6 | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | Cannot scroll through a note while editing it — notes with >1000 words are inaccessible below the fold. | Set overflow-y: auto on the note editor textarea/container. | Manual: open note with 1000+ words, verify scrolling works in edit mode. | Pending | v1.2.0
CU-004 | Remove Blue Color From Dark Theme | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 4 | React Web, Design System | frontend-web/src/design-system/tokens/ | https://app.clickup.com/t/86d27kutb | 2026-03-01 | 2026-03-08 | 7 | Gopinath R | Blue accent color bleeds into dark theme — should use a neutral or theme-appropriate color instead. | Updated --nds-* color tokens for dark theme, replaced blue with appropriate dark-mode accent. | Visual review in dark mode across all screens. | Pending | v1.2.0
CU-005 | Don't Show 'No Details Provided' / 0 for Empty Fields | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 4 | React Web | frontend-web/src/components/TaskDetailModal.jsx | https://app.clickup.com/t/86d1x1p62 | 2026-02-08 | 2026-03-08 | 28 | Gopinath R | Task detail view shows 'No details provided' and '0 files' as explicit text when fields are empty — should be hidden or shown as a subtle placeholder. | Conditionally hide empty field labels; show placeholder only on hover/focus. | Visual check: create task with no description and no attachments — verify no awkward placeholder text. | Pending | v1.1.0
CU-006 | Remove Task Type (Study, Watch) From Task Creation | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 4 | React Web | frontend-web/src/components/Tasks.jsx | https://app.clickup.com/t/86d1x1nw3 | 2026-02-08 | 2026-03-08 | 28 | Gopinath R | Task creation form shows a 'Type of task' dropdown (Study, Watch, etc.) that is confusing and unnecessary — activity types belong to sessions, not tasks. | Removed task type field from AddTaskModal and task creation API payload. | Create a task — verify no type dropdown appears. | Pending | v1.1.0
CU-007 | Need Notes Tab Feature | Frontend Web | New Feature | ClickUp | User | High | Resolved | Sprint 3 | Backend API, Database, React Web | frontend-web/src/components/NotesPage.jsx, backend/routes/notes.js | https://app.clickup.com/t/86d1umz1y | 2026-02-03 | 2026-03-08 | 33 | Gopinath R | Users need a dedicated Notes tab to create, organize, and retrieve study notes with folder structure and tags. | Built full notes feature: NotesPage.jsx, note folders, tags, inter-note linking, backend notes + note_folders + note_links routes. | Create note, add to folder, tag it, link to another note, search — all verified. | Pending | v1.1.0
CU-008 | Need Session Add Button in History Tab | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 2 | React Web | frontend-web/src/components/Timeline.jsx | https://app.clickup.com/t/86d1u9qz9 | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | No visible button to add a new study session from the history/timeline tab — users had no way to log sessions from this view. | Added Add Session floating action button to Timeline tab. | Tap Add Session → session modal opens → session saved and appears in timeline. | Pending | v1.0.0 | Tagged 'bug' in ClickUp
CU-009 | Link Tasks and Sessions to Goals | Frontend Web | New Feature | ClickUp | User | Medium | Resolved | Sprint 3 | Backend API, React Web | frontend-web/src/components/GoalsPage.jsx, backend/routes/goals.js | https://app.clickup.com/t/86d1u4atp | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | Users need to associate tasks and study sessions with specific goals to track goal progress automatically. | Added goal_tasks and goal_sessions linking in DB + UI to attach/detach from goal detail view. | Link task to goal → verify it shows in goal detail and counts toward progress. | Pending | v1.1.0
CU-010 | Need Goal Edit Option | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 3 | React Web | frontend-web/src/components/GoalsPage.jsx | https://app.clickup.com/t/86d1u4aq4 | 2026-02-01 | 2026-03-08 | 35 | Gopinath R | Goals could be created but not edited — no edit button or inline editing in the goals list. | Added edit modal to GoalsPage with pre-filled fields and PUT /api/goals/:id endpoint. | Edit goal title, deadline, description — verify changes saved and reflected in list. | Pending | v1.1.0
CU-012 | Goals Feature Implementation | Frontend Web | New Feature | ClickUp | User | Medium | Resolved | Sprint 3 | Backend API, Database, React Web | frontend-web/src/components/GoalsPage.jsx, backend/routes/goals.js, backend/database.js | https://app.clickup.com/t/86d1tk0z6 | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Initial implementation of Goals tab — users needed to set, track, and manage long-term study objectives. | Created goals DB table, full CRUD API, GoalsPage component with progress tracking. | Create goal, link sessions/tasks, mark complete — all flows verified. | Pending | v1.0.0 | Tagged 'enchance' in ClickUp
CU-016 | Add Button Showing in Wrong Location (Home / Profile Tab) | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/App.jsx, frontend-web/src/App.css | https://app.clickup.com/t/86d1tc1zy | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Floating add button was visible on Home and Profile tabs where it had no function — caused confusion. | Conditionally rendered add button only on tabs where it's relevant (Tasks, Sessions). | Navigate to Home and Profile — no add button visible. Tasks tab — button shown. | Pending | v1.0.0 | Tagged 'home tab', 'profile tab' in ClickUp
CU-017 | Email ID Showing Incorrectly in Profile Tab | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/components/ProfilePage.jsx | https://app.clickup.com/t/86d1tc1z3 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Profile tab was displaying a wrong or undefined email address for the logged-in user. | Fixed JWT payload read in profile component to correctly extract user.email. | Login, navigate to Profile — email matches account email. | Pending | v1.0.0 | Tagged 'profile tab' in ClickUp
CU-018 | Add Note Form Is Inconsistent | Frontend Web | UX | ClickUp | User | Low | Resolved | Sprint 1 | React Web | frontend-web/src/components/NotesPage.jsx | https://app.clickup.com/t/86d1tc0u3 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Add note form had inconsistent spacing, label alignment, and input sizing compared to other forms in the app. | Redesigned form to use design system tokens and match other modal forms. | Visual review against Tasks and Sessions modals for consistency. | Pending | v1.0.0
CU-019 | Add Task Button Overlay Drops Below Dashboard | Frontend Web | Bug | ClickUp | User | Medium | Resolved | Sprint 1 | React Web | frontend-web/src/components/Tasks.jsx, frontend-web/src/components/Tasks.css | https://app.clickup.com/t/86d1tc07f | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Floating 'Add Task' button was rendered below the content area on some screen sizes, hidden behind the dashboard. | Fixed z-index and position: fixed to keep button visible at all scroll positions. | Scroll task list to bottom — add button remains visible and tappable. | Pending | v1.0.0 | Tagged 'bug', 'tasks tab' in ClickUp
CU-020 | Delete Button Not Working for Tasks | Frontend Web | Bug | ClickUp | User | High | Resolved | Sprint 1 | React Web, Backend API | frontend-web/src/components/Tasks.jsx, backend/routes/tasks.js | https://app.clickup.com/t/86d1tbzr1 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Delete button on task cards was unresponsive — clicking did nothing, tasks couldn't be removed. | Fixed DELETE /api/tasks/:id handler and wired delete button to API call with confirmation. | Create task, click delete, confirm — task removed from list and DB. | Pending | v1.0.0 | Tagged 'tasks tab' in ClickUp
CU-021 | Swipe Right to Delete Tasks | Frontend Web | Enhancement | ClickUp | User | Medium | Resolved | Sprint 4 | React Web | frontend-web/src/components/BidirectionalSwipeCard.jsx | https://app.clickup.com/t/86d1tbuxc | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Users requested swipe-right gesture to quickly delete tasks on mobile, instead of tapping into the detail modal. | Implemented BidirectionalSwipeCard with right-swipe delete and left-swipe complete gestures. | Swipe right on task card — delete confirmation appears and task is removed. | Pending | v1.1.0 | Tagged 'enchance' in ClickUp
CU-022 | No Session Add Button in History Tab (Backend List) | Frontend Web | Bug | ClickUp | User | Medium | Open | Backlog | React Web | frontend-web/src/components/Timeline.jsx | https://app.clickup.com/t/86d1tdavq | 2026-01-30 |  |  |  | Duplicate open ticket: no Add Session button visible in history/timeline tab. Marked as 'mobile ui bugs' in ClickUp backend list — may need re-verification in latest build. |  |  | Not Started |  | Duplicate of CU-008 which shows resolved — needs re-verification

## Security
Security — 1 issue(s)
Issue ID | Title | Category | Sub-Category | Source | Found By | Priority | Status | Sprint | Component | Affected Files | ClickUp Link | Created Date | Resolved Date | Resolution (days) | Resolved By | Description | Solution Applied | Testing Done | Deployment Status | Version | Notes
003 | Secure Vault — Encrypted Personal Details Storage | Security | New Feature | User Report | Developer | High | Resolved | Sprint 2 | Backend API, Database, React Web | backend/database.js, backend/utils/encryption.js, backend/routes/notes.js, frontend-web/src/components/VaultPage.jsx, frontend-web/src/components/VaultUnlockModal.jsx, frontend-web/src/components/AppLock.jsx, frontend-web/src/contexts/SecurityContext.jsx | https://app.clickup.com/t/86d1uwmu2 | 2026-02-15 | 2026-02-15 | 1 | Development Team | Users needed secure storage for sensitive personal data (bank details, personal numbers, credentials) with encryption at rest. | Extended notes system with AES-256-GCM encryption + PBKDF2 key derivation (100k iterations). Added VaultPage UI with auto-lock after 5 minutes. Password never stored. | Encryption/decryption cycle, password derivation, auth tag validation, auto-lock, error handling | Pending | v1.1.0 | Master password is NOT recoverable by design

## Flutter Mobile
Flutter Mobile — 18 issue(s)
Issue ID | Title | Category | Sub-Category | Source | Found By | Priority | Status | Sprint | Component | Affected Files | ClickUp Link | Created Date | Resolved Date | Resolution (days) | Resolved By | Description | Solution Applied | Testing Done | Deployment Status | Version | Notes
UI-01 | Touch Targets Too Small (<44px) | Flutter Mobile | Accessibility | AI Analysis | AI Assistant | Critical | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/ui/widgets/vela_modal.dart, vela_flutter/lib/ui/widgets/vela_input.dart, vela_flutter/lib/ui/widgets/vela_button.dart, vela_flutter/lib/ui/screens/shared/app_shell.dart, vela_flutter/lib/core/theme/app_spacing.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Multiple interactive elements are below WCAG 2.5.5 minimum 44x44px touch target. Modal close=32px, bottom nav=36px tall, inputs=40px. | Wrapped modal close button, nav items, inputs, and buttons in ConstrainedBox(BoxConstraints(minWidth: 44, minHeight: 44)). Added AppSpacing.minTouchTarget = 44.0 token for future use. | Inspect widget tree: every interactive element shows minWidth/minHeight = 44. Test on physical device with finger — no accidental mis-taps. | Pending |  | WCAG Level A violation — blocks accessibility certification
UI-02 | Bottom Nav Text Too Small | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/core/theme/app_typography.dart, vela_flutter/lib/ui/screens/shared/app_shell.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Bottom navigation label text is too small to read comfortably on mobile screens. | Added AppTypography.fontSizeNavLabel = 11.0 and navLabel() style factory with fontWeight always weightSemibold (w600). app_shell.dart uses navLabel() for all nav items. | Open app on device, check bottom nav labels are clearly legible at arm's length. Verify all labels (active and inactive) render at 11px w600. | Pending
UI-03 | Missing Onboarding Flow | Flutter Mobile | UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/shared/onboarding_tooltips.dart, vela_flutter/lib/app.dart, vela_flutter/lib/core/storage/local_storage.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | No onboarding screens to guide new users through creating a subject and logging their first session. | OnboardingTooltips widget (3-step walkthrough: swipe gestures, camera, share target) wired into app.dart via _OnboardingOverlay in the MaterialApp.router builder. Shown once per device using LocalStorage.hasSeenOnboarding flag. Respects OS reduced-motion preference. | Clear app data, launch fresh, verify 3-step tooltip sequence appears. Complete walkthrough, relaunch — confirm tooltips do not reappear. Enable OS reduced motion — confirm overlay is skipped. | Pending
UI-04 | No Back-Button Navigation | Flutter Mobile | Navigation | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/widgets/detail_header.dart, vela_flutter/lib/ui/screens/tasks/task_detail_modal.dart, vela_flutter/lib/ui/screens/sessions/add_session_modal.dart, vela_flutter/lib/ui/screens/notes/add_note_modal.dart, vela_flutter/lib/ui/screens/tasks/add_task_modal.dart, vela_flutter/lib/ui/screens/attachments/add_attachment_modal.dart, vela_flutter/lib/ui/screens/goals/add_goal_modal.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Detail screens lack a visible back button, relying solely on the Android hardware back gesture. | DetailHeader widget with ≥ 44px back button added to task_detail_modal.dart. Close buttons with ConstrainedBox(minWidth: 44, minHeight: 44) and Semantics labels added to all modal title rows in add_session_modal.dart, add_note_modal.dart, add_task_modal.dart, add_attachment_modal.dart, and add_goal_modal.dart. | Open each modal, verify close button is visible and tap target is at least 44×44px. Verify VoiceOver/TalkBack announces 'Close' button. Tap close — confirm modal dismisses correctly. | Pending
UI-05 | Share Modal — No Active Subject Indicator | Flutter Mobile | UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/attachments/share_receive_screen.dart (new), vela_flutter/lib/ui/navigation/app_router.dart, vela_flutter/lib/main.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | When sharing content from another app to Vela, the modal doesn't show which subject is currently active. | Created ShareReceiveScreen that handles share_handler intents. Displays active subject as a prominent green badge (or an amber warning when no subject is selected). User can save as Task or Attachment. Route /share-receive added to GoRouter outside the shell. main.dart detects share intent at startup and overrides initialLocationProvider to navigate there directly. | Share a URL from Chrome/YouTube to Vela. Verify ShareReceiveScreen opens. Verify active subject badge shows the correct subject name. Remove active subject, reshare — verify amber warning appears. Tap 'Task' — confirm task created in tasks screen. Tap 'Attachment' — confirm attachment saved in attachments screen. | Pending
UI-06 | Generic / Unhelpful Error Messages | Flutter Mobile | UX | AI Analysis | AI Assistant | High | Resolved | Backlog | Flutter App | vela_flutter/lib/core/utils/error_messages.dart, vela_flutter/lib/ui/widgets/vela_error_message.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/goals/add_goal_modal.dart, vela_flutter/lib/ui/screens/tasks/add_task_modal.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Error states show generic messages that don't tell the user what went wrong or what to do next. | Populated error_messages.dart with specific actionable strings per resource; replaced all generic catch-block texts across goals, tasks, notes, sessions screens; added VelaScreenError full-screen error widget; wired inline title error in add_task_modal using VelaInput error prop. | Manually trigger load failure on GoalsScreen — should show 'Couldn't load goals. Pull down to retry.' Submit AddTaskModal with empty title — should show inline error text below field. Trigger delete failure — should show specific SnackBar message. | Pending
UI-07 | Skeleton Loading States Missing | Flutter Mobile | Performance / UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/widgets/vela_skeleton.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/tasks/tasks_screen.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart, vela_flutter/lib/ui/screens/attachments/attachments_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | List screens show a blank/spinner while loading instead of skeleton placeholder cards. | Completed vela_skeleton.dart with VelaSkeletonGoalCard, VelaSkeleton factory class (card/listItem/text helpers), and _VelaSkeletonListItem. Replaced CircularProgressIndicator in GoalsScreen with 4x VelaSkeletonGoalCard. Tasks/Notes/Sessions/Attachments screens were already wired; confirmed consistent. Shimmer uses LinearGradient tween; respects MediaQuery.disableAnimations for reduced motion. | Open GoalsScreen with slow/offline connection — should show 4 goal-shaped skeleton cards instead of spinner. Enable OS reduce-motion — shimmer animation should stop, placeholders remain visible as flat fills. Confirm all 5 screens (tasks, notes, sessions, attachments, goals) show skeletons on load. | Pending
UI-08 | Haptic Feedback Missing | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | Low | Resolved | Backlog | Flutter App | vela_flutter/lib/core/utils/haptics.dart, vela_flutter/lib/ui/widgets/vela_button.dart, vela_flutter/lib/ui/screens/tasks/tasks_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Actions like completing a task or saving a session don't trigger haptic feedback on mobile. | Added lightTap(), mediumImpact(), heavyImpact(), and error() alias methods to VelaHaptics in haptics.dart, each try/catch guarded and gated by _isSupported. VelaButton already fires VelaHaptics.light() on press; tasks_screen already fires VelaHaptics.success() on complete and VelaHaptics.heavy() on delete — confirmed wired. | On a physical Android device: tap any VelaButton — light tap should be felt. Swipe a task card right (complete) — vibration should fire. Swipe a task card left (delete) — heavier vibration should fire. Run on web/desktop — no crash, haptics silently skipped. | Pending
UI-09 | Reduced Motion Not Supported | Flutter Mobile | Accessibility | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/core/utils/motion_preferences.dart, vela_flutter/lib/core/theme/app_animations.dart, vela_flutter/lib/ui/widgets/vela_modal.dart, vela_flutter/lib/app.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Animations do not respect the device's 'Reduce Motion' accessibility setting. | MotionPreferences.of(context) reads MediaQuery.disableAnimations. AppAnimations.baseOrNone/fastOrNone/slowOrNone return Duration.zero when reduced motion is enabled. VelaModal.show() and AnimatedContainer use these helpers; app.dart propagates the flag to onboarding overlay. | Enable 'Remove animations' (Android) or 'Reduce Motion' (iOS). Open app and verify: modals appear instantly, no fade/slide animations, onboarding overlay is skipped. | Pending |  | WCAG 2.3.3 — Animation from Interactions
UI-10 | Swipe Gesture Affordance Missing | Flutter Mobile | Mobile UX | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/tasks/tasks_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Swipeable task cards have no visual hint that they can be swiped (no drag indicator or peek animation). | Added _SwipeAffordance widget with pulsing green/red edge gradient overlays on the first active card, shown until the user first swipes (stored via localStorageProvider). Added SingleTickerProviderStateMixin and a TweenSequence peek animation controller to _TasksScreenState that translates the first card -12px then +12px then back to 0 over 300ms on first load; skipped when MediaQuery.disableAnimations is true (Issue 09 compliance). After first swipe, both the gradient overlay and peek animation are permanently dismissed. | Fresh install (or clear SharedPreferences): open tasks screen with at least one task — first card should animate left-right briefly, then show green/red edge gradients. Swipe the card — gradients disappear and don't return on next launch. Enable OS Reduce Motion — peek animation should not play; static gradients still visible. | Pending
UI-11 | Spacing Inconsistencies Across Screens | Flutter Mobile | Design System | AI Analysis | AI Assistant | Medium | Resolved | Backlog | Flutter App, Design System | vela_flutter/lib/ui/screens/profile/profile_screen.dart, vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/notes/notes_screen.dart, vela_flutter/lib/core/theme/app_spacing.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Padding and margin values are inconsistent across screens — some use 8px, 12px, 16px ad-hoc instead of design tokens. | Replaced all hardcoded padding/margin values in profile_screen.dart, goals_screen.dart, and notes_screen.dart with AppSpacing tokens (s1-s12). Added AppSpacing import to all three files. notes_screen FAB clearance updated from hardcoded 80 to AppSpacing.fabClearance + MediaQuery.of(ctx).padding.bottom. tasks_screen.dart was already clean with AppSpacing tokens. | Visual review of all four screens in light and dark mode on a physical device. Confirm consistent 16px (s4) horizontal padding on all list/card containers. Confirm FAB does not overlap the last list item on iPhone X+ and Android gesture nav devices. No pixel overflow or clipped content. | Pending
CU-013 | Share Option Not Available in Production App | Flutter Mobile | Bug | ClickUp | User | High | Resolved | Sprint 2 | Flutter App, DevOps | vela_flutter/android/AndroidManifest.xml | https://app.clickup.com/t/86d1tff5v | 2026-01-31 | 2026-03-08 | 36 | Gopinath R | Share-to-Vela feature (share YouTube links from other apps) was missing from the production APK — intent filter not in release build. | Added share intent filter to AndroidManifest.xml and rebuilt production APK. | Share YouTube link from Chrome → Vela appears in share sheet → link captured. | Deployed | v1.0.0
CU-014 | Basic Share Feature Implementation | Flutter Mobile | New Feature | ClickUp | User | Medium | Resolved | Sprint 2 | Flutter App | vela_flutter/android/AndroidManifest.xml, vela_flutter/lib/ | https://app.clickup.com/t/86d1tcz85 | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Initial implementation of Android share target — receive URLs and text from other apps and save as attachments in Vela. | Registered Android share intent filter, built share receive screen to capture and save shared content. | Share from browser, YouTube, and notes app — all content captured and saved. | Deployed | v1.0.0
CU-015 | Mobile APK Production Blank Screen Issue | Flutter Mobile | Bug | ClickUp | User | High | Resolved | Sprint 1 | Flutter App, DevOps | vela_flutter/lib/app.dart | https://app.clickup.com/t/86d1tcbnt | 2026-01-30 | 2026-03-08 | 37 | Gopinath R | Production APK showed a blank white screen on launch — app failed to initialize correctly in release mode. | Fixed release build config, ensured assets bundled correctly, resolved null-safety issues that only surfaced in release mode. | Install release APK on physical device, verify app loads correctly. | Deployed | v1.0.0
UI-12 | Sessions Not Loading on Timeline Screen | Flutter Mobile | Bug Fix | Manual Testing | Flutter Investigator Agent | Critical | Resolved | Backlog | Flutter App | vela_flutter/lib/data/repositories/progress_repository.dart, vela_flutter/lib/providers/progress_provider.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Sessions tab permanently shows loading/error state and never displays sessions. getSessions() called ApiConstants.sessions (/progress/sessions) — a route that does not exist in the backend. Even if the URL were correct, response.data was cast directly as List, but the real endpoint GET /api/progress/:subject_id returns { sessions: [...], topics: [...], revisionItems: [...], pagination: {...} } — sessions is a nested key, not the root value. getTopics() had the same two bugs (/progress/topics + response.data as List). The provider called three separate Future.wait requests all hitting the same endpoint, tripling network traffic. | Added getProgress(subjectId) method to ProgressRepository that calls GET /api/progress/:subjectId and returns the full Map. getSessions() and getTopics() now delegate to getProgress() and extract response.data['sessions'] and response.data['topics'] respectively. ProgressNotifier.loadProgress() refactored to call getProgress() once and unpack sessions + topics from a single network response. | Open Sessions tab with an active subject — sessions list should render. Open network inspector and confirm exactly one GET /api/progress/:id request fires on load (not three). Pull-to-refresh and re-open — list reloads correctly. | Pending |  | Backend endpoint GET /api/progress/:subject_id does NOT use the standard { data: [], pagination: {} } envelope — it uses top-level keys. This is the only progress endpoint that exists for subject-scoped data.
UI-13 | Session cards not tappable — no detail view | Flutter Mobile | Bug Fix | Interaction Completeness Audit | Flutter Investigator Agent | High | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart (new), vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Tapping a session card on the Timeline screen did nothing. _SessionCard had onEdit and onDelete callbacks but no onTap for a detail view. Users expect tapping a card to open its detail — the missing interaction was identified by the Step 3 Interaction Completeness Audit. | Created SessionDetailModal (modelled on TaskDetailModal) showing activity type, date, duration, topics, full notes, URL/YouTube thumbnail, revision badge, and Edit/Delete actions with confirmation dialog. Added onTap prop to _SessionCard, wrapped VelaCard in GestureDetector, added _showSessionDetail() to _TimelineScreenState, and wired onTap in the SliverList builder. | Tap a session card on the Timeline screen — SessionDetailModal opens with full session info. Tap Edit — modal closes and AddSessionModal opens pre-filled. Tap Delete — confirmation dialog appears; confirm closes modal and removes session. Slidable swipe-to-delete and inline Edit/Delete buttons still work independently. | Pending
UI-14 | Session goal badge missing; attachment stub misleading | Flutter Mobile | Bug Fix | Web Parity Review | Flutter Investigator Agent | Medium | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | Web parity review against Timeline.jsx found two gaps. (1) When a session has a goal_id, the web card shows a teal goal badge with the linked goal title. Neither _SessionCard nor SessionDetailModal showed this — users had no way to see which goal a session contributed to. (2) SessionDetailModal's Attachments section showed an 'Add Attachment' button that fired showSnackBar('coming soon') — actively misleading users into thinking they could add attachments when the feature is not implemented. | Fix 1 — Goal badge in SessionDetailModal: converted StatelessWidget to ConsumerWidget, resolved goalTitle via ref.watch(goalsProvider), and added a VelaBadgeVariant.success badge (flag icon + truncated title, max 140px) after the revision badge in the meta Wrap, guarded by if (goalTitle != null). Fix 2 — Attachment stub removal: replaced the OutlinedButton/snackbar with a read-only display — muted 'No attachments' text when count is 0, or a VelaBadge with paperclip icon and count when attachments exist. Fix 3 — Goal badge on _SessionCard: added optional goalTitle String? prop, resolved at SliverList build time via ref.watch(goalsProvider) (keeps _SessionCard a plain StatelessWidget), and rendered a success badge after the revision badge in the activity type row. | Create a session linked to a goal. Open the Sessions tab — _SessionCard should show a green flag badge with the goal title next to the revision badge. Tap the card — SessionDetailModal should show the same badge in the meta row. Open a session with no goal — no badge appears. Open the modal for a session with 0 attachments — 'No attachments' muted text appears instead of the Add Attachment button. For a session with attachments the count badge renders. No snackbar fires in either case. | Pending
UI-15 | SessionDetailModal 'Add Attachment' button fires no feedback | Flutter Mobile | Bug Fix | Task — Fix non-functional button | Flutter Investigator Agent | Low | Resolved | Backlog | Flutter App | vela_flutter/lib/ui/screens/sessions/session_detail_modal.dart |  | 2026-03-22 | 2026-03-22 | 0 | Flutter Investigator Agent | The '+ Add Attachment' button in SessionDetailModal had an empty onPressed: () { // TODO } lambda. Tapping it produced zero visual feedback — no snackbar, no navigation, no modal. Web parity check confirmed Timeline.jsx has no equivalent button at all (attachment_count is display-only). Backend progress.js has no writable endpoint for session-attachment linking. The feature does not exist on any platform, so the button was silently swallowing taps. | Replaced the empty onPressed lambda with a ScaffoldMessenger snackbar ('Attachment linking for sessions is coming soon.', 2-second duration). The button remains visible so users know the feature is planned, but every tap now produces visible feedback. No API calls, no navigation. | Open any session detail modal. Tap '+ Add Attachment'. A snackbar should appear at the bottom of the screen with the 'coming soon' message and dismiss after 2 seconds. No crash, no silent swallow. | Pending

## ClickUp Issues
ClickUp Issues — Fetched 2026-03-22 ¦ Lists: TaskApp - mobile UI, TaskApp - Backend
ClickUp ID | Task Name | Status | Priority | List | Tags | URL
86d28hqa6 | Vela App: No edit option for attachments | new issue | normal | TaskApp - mobile UI |  | https://app.clickup.com/t/86d28hqa6
86d27kyx0 | Note not saving after creation — disappears on back | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d27kyx0
86d27kyv6 | Can't scroll through a long note while editing | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d27kyv6
86d27kutb | Need to remove the blue color from dark theme | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d27kutb
86d1z2736 | Need to store skills | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1z2736
86d1x1qdu | Task shouldn't complete if subtasks are still there | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1x1qdu
86d1x1p62 | Don't show 'No details provided', 0 for no files | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1x1p62
86d1x1nw3 | Remove type of task (study, watch) | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1x1nw3
86d1vpb9y | Need to alter UI | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1vpb9y
86d1uwmu2 | Option to store personal details (Secure Vault) | resolved | low | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1uwmu2
86d1umz1y | Need notes tab feature | resolved | high | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1umz1y
86d1u9qz9 | Need session add button | resolved | normal | TaskApp - mobile UI | bug | https://app.clickup.com/t/86d1u9qz9
86d1u4atp | Can link tasks and sessions to goals | resolved | normal | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1u4atp
86d1u4aq4 | Need goal edit option | resolved | high | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1u4aq4
86d1tnnwv | Goals feature not working in production | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1tnnwv
86d1tk0z6 | Goals Feature Implementation | resolved |  | TaskApp - mobile UI | enchance | https://app.clickup.com/t/86d1tk0z6
86d1tff5v | Share option not available in production app | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1tff5v
86d1tcz85 | Need to implement basic share feature | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1tcz85
86d1tcbnt | Mobile APK production blank screen issue | resolved |  | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1tcbnt
86d1tc1zy | Add button showing (home/profile tab) | resolved |  | TaskApp - mobile UI | home tab, profile tab | https://app.clickup.com/t/86d1tc1zy
86d1tc1z3 | Email ID showing wrongly in profile tab | resolved |  | TaskApp - mobile UI | profile tab | https://app.clickup.com/t/86d1tc1z3
86d1tc1m8 | No button to add sessions in history tab | resolved | normal | TaskApp - mobile UI |  | https://app.clickup.com/t/86d1tc1m8
86d1tc0u3 | Add note form is inconsistent | resolved |  | TaskApp - mobile UI | tasks tab | https://app.clickup.com/t/86d1tc0u3
86d1tc07f | Add task button overlay gone below dashboard | resolved |  | TaskApp - mobile UI | bug, tasks tab | https://app.clickup.com/t/86d1tc07f
86d1tbzr1 | Delete button not working for tasks | resolved |  | TaskApp - mobile UI | tasks tab | https://app.clickup.com/t/86d1tbzr1
86d1tbuxc | Swipe right to delete tasks | resolved | normal | TaskApp - mobile UI | enchance | https://app.clickup.com/t/86d1tbuxc
86d1tdavr | Mobile APK blank screen (deployment issues) | deployment issues |  | TaskApp - Backend |  | https://app.clickup.com/t/86d1tdavr
86d1tdavq | No button to add sessions in history tab | mobile ui bugs |  | TaskApp - Backend | sessions tab | https://app.clickup.com/t/86d1tdavq
86d1tdava | Swipe right to delete tasks (UI enhancement) | ui enhancements | normal | TaskApp - Backend | enchance | https://app.clickup.com/t/86d1tdava
86d1tdavm | Add button showing (home/profile) | resolved |  | TaskApp - Backend | home tab, profile tab | https://app.clickup.com/t/86d1tdavm
86d1tdavk | Delete button not working for tasks | resolved |  | TaskApp - Backend | tasks tab | https://app.clickup.com/t/86d1tdavk
86d1tdavj | Email ID showing wrongly in profile tab | resolved |  | TaskApp - Backend | profile tab | https://app.clickup.com/t/86d1tdavj
86d1tdavf | Add note form is inconsistent | resolved |  | TaskApp - Backend | tasks tab | https://app.clickup.com/t/86d1tdavf
86d1tdav8 | Add task button overlay gone below dashboard | resolved |  | TaskApp - Backend | bug, tasks tab | https://app.clickup.com/t/86d1tdav8

## Statistics
Overview
Total Issues | 41
Resolved | 39
Open | 2
Completion Rate | 95%
By Status
Open | 2
Resolved | 39
By Priority
Critical | 2
High | 15
Medium | 19
Low | 5
By Category
Backend | 3
Flutter Mobile | 18
Frontend Web | 19
Security | 1
Discovered By
AI Assistant | 11
Developer | 4
Flutter Investigator Agent | 4
User | 22
Open Issues by Priority
Medium | 2