## Summary Dashboard
VELA Improvements — Summary Dashboard
Improvement Counts by Tier
Tier 1 — Quick Win | 3 improvements
Tier 2 — Wire Backend | 6 improvements
Tier 3 — New Feature | 3 improvements
Priority Breakdown
Critical | 1 improvements
High | 7 improvements
Medium | 4 improvements
Backend / DB Impact Summary
Improvements needing NO new endpoint | 9 / 12
Improvements needing NO new DB table | 10 / 12
Total improvements | 12

## All Improvements
VELA — Manifest Coach Feature Improvements Roadmap
Generated from codebase analysis · 12 improvements · Tiers 1–3
ID | Title | Tier | Category | Priority | Effort | Impact | New Endpoint? | New DB Table? | API Changes | DB Changes | Flutter Impact | Web Impact | Status
IMP-001 | Display Study Streak Badge | Tier 1 — Quick Win | Flutter Mobile | High | Low (1–2 days) | High | No | No | None | None | Yes — timeline_screen.dart, profile_screen.dart | Optional — can mirror in ProfilePage.jsx | Pending
IMP-002 | Goal Progress Bar (% toward target hours) | Tier 1 — Quick Win | Flutter Mobile + React Web | High | Low (1–2 days) | High | No | No | None (data already in response — verify total_minutes field) | None | Yes — goals_screen.dart / GoalCard widget | Yes — GoalsPage.jsx | Pending
IMP-003 | Task Completion Celebration Animation | Tier 1 — Quick Win | Flutter Mobile + React Web | Medium | Low (1 day) | Medium | No | No | None | None | Yes — tasks_screen.dart | Yes — Tasks.jsx | Pending
IMP-004 | Surface Journal Feature (Goal-Linked Journaling) | Tier 2 — Wire Backend | React Web + Flutter Mobile | Critical | Medium (3–5 days) | Very High | No (already exists) | No (journal_entries table already exists) | None — backend/routes/journal.js already mounted and complete | None | Yes — new journal_repository.dart, journal_provider.dart, journal UI | Yes — GoalDetailModal.jsx gets Journal tab | Pending
IMP-005 | Contextualized AI Ask Coach | Tier 2 — Wire Backend | React Web + Flutter Mobile + Backend | High | Medium (2–3 days) | High | No (enhance existing /api/ask) | No | Non-breaking — add optional `context` field to POST /api/ask body | None | Yes — ask_screen.dart, ask_repository.dart | Yes — AskPage.jsx | Pending
IMP-006 | Flutter Goal Detail Modal (Parity Gap) | Tier 2 — Wire Backend | Flutter Mobile | High | Medium (2–3 days) | High | No | No | None | None | Yes — goals_screen.dart + new goal_detail_modal.dart | None | Pending
IMP-007 | Morning Intention Modal (Daily Focus Setter) | Tier 3 — New Feature | Flutter Mobile + React Web | High | Medium (3–4 days) | Very High | No (POST /api/journal already exists) | No (ALTER existing journal_entries) | Minor — POST /api/journal gains optional type field (non-breaking) | Add `type VARCHAR(50) DEFAULT 'reflection'` to journal_entries (nullable safe) | Yes — app_shell.dart, new intention_modal.dart | Yes — App.jsx, new MorningIntentionModal.jsx | Pending
IMP-008 | Post-Session Reflection Prompt | Tier 3 — New Feature | Flutter Mobile + React Web | Medium | Low–Medium (2 days) | High | No | No | None | None (uses existing journal_entries table) | Yes — add_session_modal.dart | Yes — wherever AddSessionModal success is handled | Pending
IMP-009 | Daily Affirmation / Motivational Banner | Tier 3 — New Feature | Flutter Mobile + React Web | Medium | Low (1 day) | Medium | No | No | None | None | Yes — tasks_screen.dart | Yes — Tasks.jsx | Pending
IMP-010 | Flutter Subtask Toggle + Completion (Parity Gap) | Tier 2 — Wire Backend | Flutter Mobile | High | Low–Medium (1–2 days) | High | No | No | None (PUT /api/tasks/:id already handles completed field) | None | Yes — task_detail_modal.dart, tasks_provider.dart | None | Pending
IMP-011 | Sessions Progress Graph in Flutter (Parity Gap) | Tier 2 — Wire Backend | Flutter Mobile | Medium | Medium (2–3 days) | Medium | No | No | None | None | Yes — timeline_screen.dart + new sessions_graph_screen.dart | None | Pending
IMP-012 | Flutter Integration Test Suite | Tier 2 — Wire Backend | Flutter Mobile | High | Medium (3–5 days) | High | No | No | None — tests consume existing API endpoints | None | Yes — integration_test/, main.dart, all screen widgets (Key additions) | No | Pending

## Technical Detail
VELA — Technical Implementation Detail
ID | Title | Description | Technical Steps | Psychology / Why
IMP-001 | Display Study Streak Badge | ProgressProvider already computes `streak`, `studyDays`, and `studyStreak` but these values are never displayed in any UI. Add a streak badge (e.g. '🔥 7-day streak') to the Timeline screen header and the Profile screen stats section. | 1. Read progress_provider.dart — confirm streak field name. 2. In timeline_screen.dart: consume ProgressProvider via ref.watch, add VelaBadge(label: '🔥 ${state.streak} day streak') in the AppBar actions. 3. In profile_screen.dart: add streak stat card alongside existing stats. 4. No backend changes needed — data already fetched. | Habit loop reinforcement (James Clear). Streak visibility drives consistency (Duolingo model).
IMP-002 | Goal Progress Bar (% toward target hours) | Goals have `target_hours` stored in DB. The goals API JOIN already returns `total_minutes` from linked study sessions. Calculate percentage = (total_minutes / (target_hours * 60)) * 100 and render a progress bar on each GoalCard. | 1. Verify backend/routes/goals.js returns total_minutes in GET / response. 2. Flutter: In GoalCard widget, add LinearProgressIndicator with value = min(totalMinutes / (targetHours * 60), 1.0). 3. Web: In GoalsPage.jsx GoalCard section, add <progress> or CSS bar element. 4. Show percentage label: '67% complete (20h / 30h target)'. | Zeigarnik Effect — visible progress gaps keep goals motivating. Expectancy Theory — seeing progress builds belief.
IMP-003 | Task Completion Celebration Animation | When a task is marked complete, nothing happens visually beyond a strikethrough. Add a brief confetti burst or checkmark animation to create a dopamine reward moment. Flutter: use the `confetti` package. Web: CSS keyframe animation or canvas confetti. | 1. Flutter: Add `confetti: ^0.7.0` to pubspec.yaml. Create ConfettiController, trigger on task toggle complete. Respect AppAnimations.reducedMotion — skip if user prefers-reduced-motion. 2. Web: On task complete in Tasks.jsx, trigger a CSS animation class for 600ms. Use @keyframes for a simple scale+fade or import canvas-confetti npm package. Wrap in prefers-reduced-motion media query check. | Operant conditioning — immediate positive reinforcement after behavior increases repetition (B.F. Skinner).
IMP-004 | Surface Journal Feature (Goal-Linked Journaling) | The journal backend is fully built (journal.js: GET, POST, PUT, DELETE, stats endpoint). The journalApi client in api.js is complete. Zero backend work needed. Build the UI layer: a Journal tab inside GoalDetailModal (web) and a journal section/screen inside GoalsScreen (Flutter). | 1. Read backend/routes/journal.js — note exact schema fields (entry_text, mood, type, goal_id). 2. Web: In GoalDetailModal.jsx add a 'Journal' tab using the existing Tabs component. Load entries via journalApi.getByGoal(goalId). Render entry list + add entry form. 3. Web: Create JournalEntry.jsx card component (date, mood, text). 4. Flutter: Create JournalRepository using DioClient (GET /api/journal/goal/:id, POST). 5. Flutter: Create JournalProvider (StateNotifier pattern matching other providers). 6. Flutter: Add journal entries section to goals detail view. 7. Both: Wire journalApi.getStats() to show mood trend on goal card. | Journaling = scripting (The Secret) + cognitive reappraisal (CBT) + self-monitoring. #1 technique across all manifestation systems.
IMP-005 | Contextualized AI Ask Coach | The Ask AI screen (web + Flutter) is a generic chat interface with no knowledge of the user. Inject a system context block before each chat message containing: active subject name, pending task count + top 3 task titles, current streak, recent session count (last 7 days), and active goals. This turns a generic chatbot into a personal study coach. | 1. In backend/routes/ask.js: Accept optional `context` field in POST body. Prepend context as a system message before the user message in the LLM call. 2. In frontend AskPage.jsx / ask_screen.dart: Before sending a message, fetch: currentSubject (from SubjectsProvider), activeTasks (top 3 from TasksProvider), streak (from ProgressProvider), recentSessions count. 3. Bundle as context object and pass to askApi.chat(messages, context). 4. Keep context injection optional — degrade gracefully if data not loaded. 5. Add manifest-coach.md system prompt content to ask.js as the AI persona. | A coach who knows your situation can coach you. Contextual AI = RAS priming + personalized feedback loop.
IMP-006 | Flutter Goal Detail Modal (Parity Gap) | Web has GoalDetailModal.jsx (full detail view, linked sessions, journal). Flutter tapping a goal does nothing — no detail view. Create GoalDetailModal as a bottom sheet matching web functionality: goal title, description, status, target date, progress bar, linked sessions list. | 1. Read frontend-web/src/components/GoalDetailModal.jsx for web spec. 2. Create goal_detail_modal.dart as a VelaModal bottom sheet. 3. Sections: Header (title, status badge, close button), Progress bar (hours_logged / target_hours), Target date chip, Description text, Linked sessions list (load via GET /api/progress/sessions?goal_id=X). 4. Wire from GoalsScreen: onTap → showModalBottomSheet(GoalDetailModal). 5. Add Edit + Delete actions in modal footer. | Goals without detail view feel abandoned. Long-term orientation requires regular goal review (Expectancy Theory).
IMP-007 | Morning Intention Modal (Daily Focus Setter) | On first app open of the day, show a fullscreen modal: 'What are you manifesting today?' with a text input and optional goal selector. Save the intention as a journal_entry with type='intention'. Dismiss until tomorrow (store last_shown_date in localStorage / SharedPreferences). Show the intention as a banner at top of Tasks screen for the rest of the day. | 1. Check backend/routes/journal.js schema — does journal_entries have a `type` column? If not: ALTER TABLE journal_entries ADD COLUMN type VARCHAR(50) DEFAULT 'reflection'; 2. Flutter: In app_shell.dart initState, check local_storage for last_intention_date. If not today, show IntentionModal as overlay after auth check. 3. Flutter: Create IntentionModal widget — title, text field, goal dropdown, Save button. On save: POST /api/journal with type='intention', store today's date in local_storage. 4. Web: In App.jsx useEffect (on mount), check localStorage for last_intention_date. If not today, render MorningIntentionModal. 5. Both: After save, show intention as a dismissable banner in Tasks screen. | Implementation intentions (Peter Gollwitzer): 'When X, I will do Y' increases follow-through by 2x. RAS priming for the day.
IMP-008 | Post-Session Reflection Prompt | After a study session is successfully logged, show a brief prompt: 'Great session! Want to note what you manifested?' with a 2-tap flow: Skip ¦ Add reflection. If Add: show a 1-field text input, save as journal_entry linked to the session (goal_id if session has one). | 1. Flutter: In add_session_modal.dart, on successful POST /api/progress/sessions, show a SnackBar/dialog: 'Session logged! Add a reflection?' with action button. 2. If tapped: show a simple bottom sheet with text field + Save. POST /api/journal with entry_text, type='reflection', goal_id (from session). 3. Web: After session save success in App.jsx or Timeline.jsx, show a lightweight modal with same prompt. 4. Both: Reflection is optional — 'Skip' dismisses with no action. | Spaced retrieval + emotional tagging. Reflecting on sessions consolidates learning memory (Cognitive psychology). Evening review habit.
IMP-009 | Daily Affirmation / Motivational Banner | Add a rotating daily affirmation/motivational quote at the top of the Tasks screen. Curated list of 30+ study/manifestation affirmations. Rotate daily using day-of-year % list.length (deterministic, same quote all day). Dismissable per-day. No backend needed — pure frontend. | 1. Create affirmations.dart / affirmations.js with curated list of 30 affirmations. 2. Deterministic selection: dayOfYear % affirmations.length. 3. Flutter: Add a VelaCard with italic quote text at top of TasksScreen ListView. Store dismissed date in local_storage — hide for rest of day if dismissed. 4. Web: In Tasks.jsx render a dismissable banner above task list. Use localStorage('affirmation_dismissed_date') to persist dismissal. | Positive self-talk primes identity-based behavior (James Clear). Daily repetition builds belief schemas (CBT affirmations).
IMP-010 | Flutter Subtask Toggle + Completion (Parity Gap) | Subtasks in Flutter TaskDetailModal are currently read-only (shown but not tappable). Web TaskDetailModal has full toggle complete + delete on each subtask. Wire subtask checkboxes to PUT /api/tasks/:id with completed=true/false. | 1. Read backend/routes/tasks.js PUT /:id endpoint — confirm it accepts completed field. 2. In task_detail_modal.dart: Wrap each subtask row in GestureDetector/InkWell. 3. On tap: call tasksProvider.toggleTaskComplete(subtaskId) — reuse existing method. 4. Update local state to reflect toggle immediately (optimistic UI). 5. Add delete icon on subtask row → call tasksProvider.deleteTask(subtaskId). | Completing subtasks = micro-wins. Momentum builds on small victories (Progress Principle — Teresa Amabile).
IMP-011 | Sessions Progress Graph in Flutter (Parity Gap) | Web has SessionsGraphModal showing study time trends over time. Flutter Timeline screen has no graph. Add a chart icon button to Timeline AppBar that opens a graph screen showing daily/weekly study minutes using fl_chart package. | 1. Add `fl_chart: ^0.68.0` to pubspec.yaml. 2. Create sessions_graph_screen.dart with BarChart or LineChart. Data source: ProgressProvider sessions grouped by date. 3. X-axis: last 14 days. Y-axis: minutes studied per day. 4. Add IconButton(icon: Icon(Icons.bar_chart)) to timeline_screen.dart AppBar. On tap: navigate to SessionsGraphScreen. | Progress visualization activates Expectancy Theory — seeing results builds belief in effort→outcome causation.
IMP-012 | Flutter Integration Test Suite | Set up the `integration_test` package to run end-to-end UI tests on a real device or emulator. Tests run against the real backend API (not mocked). Cover 6 critical user flows: login, add task, log study session, switch subject, add attachment, and create note. Add Key() identifiers to critical widgets to make them findable in tests. | 1. Add `integration_test` and `flutter_test` to pubspec.yaml dev_dependencies. 2. Create integration_test/ directory with app_test.dart as the entry point. 3. Add Key() identifiers to: login form fields (email, password), bottom nav tabs, FABs, and modal action buttons across all screens. 4. Write testWidgets for: - Login flow: enter credentials → reach home screen. - Task creation: tap FAB → fill modal → task appears in list. - Session log: fill session form → appears in timeline. - Subject switch: switch subject → tasks/sessions update. - Attachment upload: pick file → appears in attachments tab. - Note creation: create note → appears in notes list. 5. Add `flutter test integration_test/` step to GitHub Actions deploy.yml. 6. Document run command in vela_flutter/README.md. | N/A — Engineering quality gate. Prevents regressions across critical user flows.

## Files Affected
VELA — Files to be Modified per Improvement
ID | Title | Files Affected
IMP-001 | Display Study Streak Badge | vela_flutter/lib/providers/progress_provider.dart, vela_flutter/lib/ui/screens/sessions/timeline_screen.dart, vela_flutter/lib/ui/screens/profile/profile_screen.dart
IMP-002 | Goal Progress Bar (% toward target hours) | vela_flutter/lib/ui/screens/goals/goals_screen.dart, frontend-web/src/components/GoalsPage.jsx, frontend-web/src/components/GoalsPage.css
IMP-003 | Task Completion Celebration Animation | vela_flutter/lib/ui/screens/tasks/tasks_screen.dart, frontend-web/src/components/Tasks.jsx, frontend-web/src/components/Tasks.css
IMP-004 | Surface Journal Feature (Goal-Linked Journaling) | backend/routes/journal.js (READ FIRST — already complete), frontend-web/src/api.js (journalApi already exists), frontend-web/src/components/GoalsPage.jsx, frontend-web/src/components/GoalDetailModal.jsx (new Journal tab), vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/data/repositories/ (new journal_repository.dart), vela_flutter/lib/providers/ (new journal_provider.dart)
IMP-005 | Contextualized AI Ask Coach | backend/routes/ask.js, frontend-web/src/components/AskPage.jsx, frontend-web/src/api.js (askApi.chat), vela_flutter/lib/data/repositories/ask_repository.dart, vela_flutter/lib/ui/screens/ask/ask_screen.dart
IMP-006 | Flutter Goal Detail Modal (Parity Gap) | vela_flutter/lib/ui/screens/goals/goals_screen.dart, vela_flutter/lib/ui/screens/goals/goal_detail_modal.dart (new file), vela_flutter/lib/data/repositories/goals_repository.dart
IMP-007 | Morning Intention Modal (Daily Focus Setter) | backend/routes/journal.js (add type='intention' support — check schema), vela_flutter/lib/ui/screens/shared/app_shell.dart, vela_flutter/lib/core/storage/local_storage.dart (store last_intention_date), frontend-web/src/App.jsx (trigger on first daily load), frontend-web/src/components/MorningIntentionModal.jsx (new), frontend-web/src/components/MorningIntentionModal.css (new)
IMP-008 | Post-Session Reflection Prompt | vela_flutter/lib/ui/screens/sessions/add_session_modal.dart, frontend-web/src/components/AddSessionModal.jsx (or wherever session is saved)
IMP-009 | Daily Affirmation / Motivational Banner | vela_flutter/lib/ui/screens/tasks/tasks_screen.dart, frontend-web/src/components/Tasks.jsx, vela_flutter/lib/core/utils/ (new affirmations.dart), frontend-web/src/utils/ (new affirmations.js)
IMP-010 | Flutter Subtask Toggle + Completion (Parity Gap) | vela_flutter/lib/ui/screens/tasks/task_detail_modal.dart, vela_flutter/lib/providers/tasks_provider.dart, vela_flutter/lib/data/repositories/tasks_repository.dart
IMP-011 | Sessions Progress Graph in Flutter (Parity Gap) | vela_flutter/lib/ui/screens/sessions/timeline_screen.dart, vela_flutter/lib/ui/screens/sessions/sessions_graph_screen.dart (new), vela_flutter/lib/providers/progress_provider.dart
IMP-012 | Flutter Integration Test Suite | vela_flutter/integration_test/app_test.dart (new), vela_flutter/pubspec.yaml, vela_flutter/lib/main.dart, .github/workflows/deploy.yml